## Slide 1
Sonata Knowledge Assistant
From POC to Production: The Full Roadmap
5 phases · Citation-grounded AI · Read-only foundation

## Slide 2
The Problem
Sonata knowledge fragmented across 4 systems
No unified query layer — answering functional questions requires manual SME cross-referencing
Upgrade assessments take 2–3 days per client (vs. 1 hour with the assistant)
Bottleneck: same ~5 senior engineers field every functional question

## Slide 3
Phase 0: POC — ✓ COMPLETE
What We Built
Single feature (searchEmployer pagination)
20–30 curated test questions
Proof: ingest → index → retrieve → cite
Cost: ~$0.11/question
Results
27/27 correct (100%)
100% accurate citations
SME Pratigya: sign-off obtained ✓
Ready to scale to all modules

## Slide 4
Phase 1: Functional Knowledge Base (Chat)
Scope
All Wiki spaces (design, arch, specs)
All Jira projects (stories, defects)
Feature/Module taxonomy (SME workshop)
Multi-turn chat interface
Delivers
Answer functional Q&A across all modules
100+ test questions (≥80% correct)
Feedback signal (up/down votes)
Timeline: 6–8 weeks (1 eng + SME)

## Slide 5
Phase 2: Code + Test Layer (Bitbucket + X-ray)
New Data
Bitbucket PR metadata (modules, merge date)
X-ray test cases + history
Entity graph: Wiki ↔ Jira ↔ PR ↔ Test
Enables
"What test coverage for feature X?"
Change traceability: feature → code → tests
Data foundation for Phase 3
Timeline: ~6 weeks

## Slide 6
Phase 3: Upgrade Impact Assessment
The Ask
Given: client, from_version, to_version
Generate: what changed, what's relevant, what's risky
Output: draft report for human sign-off
Impact: 2–3 days → 1 hour per client
New Pieces
Client profile data (version, modules used)
Risk/impact scoring model
Version-diff engine (what changed)
Word/PDF export for client hand-off
Timeline: ~8 weeks

## Slide 7
Phase 4: Voice Interface + Full Timeline
Phase 4: Voice
STT input + TTS output · Response formatting (spoken sentences, natural numbers) · Opt-in per response
P0 ✓ 3–4w
P1 6–8w
P2 6w
P3 8w
P4 4w
Effort per phase (indicative)
P1: 1 eng + SME (long pole: taxonomy workshop) · P2: 1 eng · P3: 1–2 engs + domain experts · P4: 0.5 eng (parallelizable)

## Slide 8
Business Value at Each Phase
Phase 1
Support/QA/BA can self-serve answers → fewer SME escalations
Phase 2
Answer technical questions about code changes & test coverage → safer support
Phase 3
Assessment: 2–3 days → 1 hour per client → 10–15 clients/year unblocked
Phase 4
Voice option for field/mobile: hands-free Q&A on client calls

## Slide 9
Key Dependencies & Risks
Phase 1 → 3: Feature/Module taxonomy (SME workshop) is the long pole
Client profile data (Phase 3): doesn't exist cleanly — requires interviews or config review
Wiki/Jira quality uneven — Phase 1 surfaces documentation debt
Version-to-trunk mapping: must validate fixVersion accuracy
Mitigation
Make escalation / "I don't know" cheap & explicit (not a failure — a feature)
Surface last-updated dates on every citation (flag stale content)
Documentation-debt backlog is valid Phase 1 output (drives wiki improvements)

## Slide 10
Next Steps: Phase 1 Kickoff
Book the Feature/Module taxonomy workshop (the critical path item)
Enumerate all Wiki spaces + Jira projects for full ingestion scope
Build Jira bulk-ingestion script
Apply cost-optimization levers (validated on Phase 0)
The Opportunity
Phase 0 proved it works: 27/27 correct, 100% cited. Phase 1 just turns that proven pattern on for every module. From there, Phases 2–4 unlock client-facing upgrade assessment.